## SCRUTINY NOTE
Plan-Capital
PROFORMA TO ACCOMPANY TO EACH BILL
1. | Serial No. of Bill |  | serial no. of this bill : 9th R.A Bill
2. | Name of Work | Name of work: Construction of Studio Apartment at Cozy Cot at LBSNAA,Mussoorie. (EFC Scheme No.12 A of 12th Five Year Plan).
3. | Agreement No. |  | 36/EE/MPD/2013-14
4. | Name of Contractor |  | Sh. Anil Dutt Sharma
5. | Estimated Amount |  | Rs. 4,90,16,914/-(Civil) Rs. 19,15,845/-(Elect.) Rs. 5,09,32,759/-
6. | Tendered Amount |  | Rs. 5,19,92,241/-(Civil) Rs. 23,18,172/-(Elect.) Rs. 5,43,10,413/-
| Percentage Under Clause-12 |  | 6.07% Above
7. | Date of commencement of work |  | 2013-10-03
8. | Stipulated date of completion |  | 2014-12-24
9. | Date of actual completion of the work completed |  | Work is in Progress
10. | Has the contractor applied for extension of time and has the application been forwarded and recommended to the EE. Do you propose any recovery for delay in completion of work? |  | yes
11. | Measurement Books.
a) | Give the number of accompanying measurement books
b) | Has the AE/EE test checked the measurements to the extent of 50%. |  | Yes please
c) | Has the EE Test Checked the measurements to the extent of 10%
d) | Has the contractor’s signature taken in the MB & Bill in taken of accountancy of measurements |  | Yes please
12 | Additions, Substitution and Deviations
a) | Have all extra/substituted items billed for been covered by proper sanctions of reference to the letter under which the substituted items statement have been sent for approval. |  | NA
b) | If part rates have been proposed have reasons been given therefore. |  | NA
c) | Are the quantities deviated beyond permissible limits? If so give reference to sanctions obtained for executing excess less quantities if any, be stated. |  | NA
d) | In the test of percentage rate tenders, reasons for excess in quantities if any |  | NO
13 | Site Order Book
a) | Has the Site Order Book been consulted before sending the bills |  | Yes and enclosed PLEASE.
b) | Has the contractor complied with all the instructions given to him through site order book? If not AE to confirm that no item of work in respect of which defects have been pointed out & which have not rectified have been measured and recorded in M.B. exte |  | Yes PLEASE
14 | Issue of materials
a) | Is recovery statement for issue of departmental materials attached? If full recovery has not been made for materials issued departmentally. |  | NA
b) | Has a statement of theoretical consumption been attached for materials? |  | Yes please
c) | If materials not stipulated. In agreements have been issued has sanction of the competent authority been obtained and the issue rates not approved. |  | NA
d) | Are there any dismantled materials? If so, have they been accounted for property in the dismantled material register? |  | NA
e) | Have unstamped dated receipts been obtained from the contractor for materials issued to him upto date? |  | NA
f) | Have necessary T.E. orders for issued of materials to contractor submitted to Divisional Office? |  | NA
15 | Excess Over Estimate:
In case up to date expenditure on the work exceeds the permissible limit of exceeds the permissible limit of excess over technical sanction has a revised estimate been submitted to Divisional Office.
16 | Recoveries
Have recoveries been proposed by the following officer and if so, has the recovery been affected.
a) | Chief Technical Examiner, amplifying the nature of observations made, and whether any recovery is called for. |  | NA
b) | Labour Enforcement Officer |  | NA
c) | Labour Officer |  | NA
d) | Any other Authorities |  | NA
e) | Has recovery been affected for T&P issued to these contractors? |  | NA
17. | If water has been supplied under Clause 31 for the work, has the recovery been made? |  | OWN ARRANGEMENT OF CONTRACTOR
18. | If T&P stipulated in the amount has been issued to the contractor has the rate of recovery been approved by EE and has the recovery been made? |  | No T&P issued to the contractor
19. | Has the contractor returned empty gully bags/bitumen drums if not, has recovery been proposed? |  | NA
20. | (In the case of final bill has the completion certificate been recorded in MB? Give reference to MB & Page No. |  | NA
21. | In the Case of final bill has the contractors signed the bill/M.B. is full and final settlement if not brass reasons may be given. |  | Yes please
22. | Whether the contractor has complied with the provisions of clause 36 of the agreement and if not to what extent. |  | Yes please
23. | Whether the contractor submitted the fortnightly labour report. |  | YES
24. | Has the bill checked by the SDC & Certificate of check recorded by him in the MB. |  | YES CHECKED & CERTIFICATE RECORDED IN THE MB.
FOR DIVISIONAL ACCOUNTANT IN DIVISION OFFICE
25. | Has the contractor's ledger been brought up to date?
26. | Has the contractor's ledger been verified before submitting bill with pass order
27. | Have we received any court attachment of advice from the Divisions etc. for recovery and if so, have they been affected in the bill?
28. | Has theoretical consumption statement been got verified by the Drawing Branch?

## bill form1-2
C.P.W.A.-26(Revised)
ukSoka py ys[kk fcy && 4059 (PLAN)- PPG
(Referred to in Paragraph 10-2-10 and 10-2-12)
Final payments must invariably be made on formats Printed on Yellow paper which should not be used for intermediate payments (For contractors this form provides for (1) advance payments (2) Payment for measurement works. The form of Account Secured advance which has been printed separately should be attached where necessary)
Division:- |  | Mussoorie Project Division, |  |  |  | Sub-division:- |  | MCSD,CPWD
Cash Book Voucher No. & date
Name of work: Construction of Studio Apartment at Cozy Cot at LBSNAA,Mussoorie. (EFC Scheme No.12 A of 12th Five Year Plan).
Name of Contractor: Anil Dutt Sharma
Serial No of this Bill |  |  |  | 9th R.A. Bill
No. & date of the previous Bill of this work |  |  |  | 8th RA BiII Vide CV no. 39 dated : 17-03-2015
Reference to Agreement No |  |  |  | 36/EE/MPD/2013-14
Date of written order to commence work |  |  |  | 2013-10-03
Date of actual completion of work |  |  |  | Work is in Progress
Account of Work Executed
S.No. | Item of works grouped under sub-head and sub work of estimate |  | Unit | Rate | Quantity executed up-to-date as per Measurment book |  | Payment on the basis of actual measurments of estimate |  | Remark
[7 empty] | Upto Date | Since Previous Bill
|  | 1 | 2 | 3 |  | 4 | 5 | 6 | 7
AS PER SHEET ENCLOSED
S.No. | Item of works grouped under sub-head and sub work of estimate |  | Unit | Rate | Quantity executed up-to-date as per Measurment book |  | Payment on the basis of actual measurments of estimate |  | Remark
[7 empty] | Upto Date | Since Previous Bill
|  | 1 | 2 | 3 |  | 4 | 5 | 6 | 7
[6 empty] | 21644248 |  | 1480349
Total Value of work done to date (A) | [5 empty] | 21644248 |  | 1480349
Deduct value of work shown on previous Bill | [5 empty] | -20163899
Net value of work since previous Bill (F) | [5 empty] | 1480349
Figure (F) in words Rupees FORTEEN LAKH EIGHTY THOUSANDS THREE HUNDRED & FORTY NINE Only.
B- When there are two or more entries in column 6 relating to each sub-head of estimate they should in …of work the account of which are kept by sub-heads to be totaled
II. Certificate & Signature
1. The measurement on which are based the entries in column 1 to 6 of account were made by SH.Manoj Kumar, JE(C) on 26-03-2014 and are recorded on page 1-38 of measurement book No CMB- 267 /MPD
2. Certified that in addition and quantity part from the quantities of work actually executed as shown in column 4 of the account I some work has actually been done in connection with several items and the value of such work (after deducting there from proportionate amount of recurred advance if any ultimately recoverable on account of the quantities of the materials used therein) is in no case less than the advance payment as per item 2 of memorandum if payment made or proposed to be made for the convenience of the contractor in anticipation.
Dated Signature of Officer (..................................................
preparing the Bill (Rank..........................................
Dated Signature of Contractor |  |  |  | **Dated Signature of Officer (..................................................
Authorising payment (Rank..........................................

## bill form 3-4
II Memorandum of Payments
[9 empty] | Rs. | P.
1. Total value of work actually measured, as per account 1, column 5 entry (A)
2. Total up-to-date, advance payment for work not yet measured, as per detailed given below.
Rs. P. |  | Rs. P.
Total as per Previous Bill ................................
(b) Since Previous bill ..................as per page ............................... ...of ....
M.B.No. ..................................................(D)
3. Total "up-to-date" secured advance on security of materials as per annexure
form (26-A) col. 8 Entry (C) ........ .......
4. Total Items (1+2+3) ........ ....... ......
5. Deduct amount withhold
Figure for work abstract | (a)From previous bill as per the last Running Account Bill ..... |  |  |  | Rs.
(b) From this bill
6. Balance i.e. "up-to-date" payments (item 4-5) -(K*)
7.Total amount of payments already made as per entry (K) of last Running Account Bill Voucher No .........of........ forwarded
| 8.Payments now to be made as detailed below : Rs. P. |  |  |  | Rs. | P.
| (a) By recovery of amount creditable to this work |  |  | (a)
Total 5 (b) + 8 (a) (G)
b) By recovery of amount creditable to other work or head of accounts
(i) Security Deposit ……..
(ii) Income Tax ………..
(iii)Education cess ………..
| (iv)Cess for H & I education ……… |  |  | (b)
(v)Sale tax …………….
(vi) CWWC …………
(vii) . . . . . . . . . . . . . .. . . . . . . . . . . . . . .
(viii) . . . . . . . . . . . . . .. . . . . . . . . . . . . . .
| (c) by Cheque |  |  | ©
Total 8 (b) + (c) (H)
Pay Rs. * b (............................................) ............ ............. .............. ...............
.............. ........... ......... ............. .............. ...............@( by cheque)
Dated Initial of Disbursing Officer
Recieved Rs.= (......................................) ................. ...................... .................. .... | [8 empty] | STAMP
............ .............. ............ . ................ ............. ............as per above memorandum of account of this work
Dated .. | [7 empty] | Signature of contractor
Paid by me vide cheque** No. |  |  |  |  | Dated..........
Dated initial of person actually making the payment
REMARKS
This space is reserved for any remarks which the disbursing officer or the Divisional Officer may wish of record in respect to the exception of the work, check of measurement of the state of contractor's amount.
Checked
Account Clerk | [5 empty] | Divisional Accountant
FOR USE IN ACCOUNTANT GENERAL'S OFFICE
Computed |  |  | Classification |  |  |  |  | Reviewed
Checked
Checked with scheduled of rates / checked with rates as per agreement |  |  | Reviewed
Auditor |  | Gazetted Officer |  |  |  |  | Superintendent

## Mest cover sheet
Mussoorie Project Division
Mussoorie Central Sub-Division
Name of work: Construction of Studio Apartment at Cozy Cot at LBSNAA,Mussoorie. (EFC Scheme No.12 A of 12th Five Year Plan).
Name of Contractor: Anil Dutt Sharma
Agmt. No. : 36/EE/MPD/2013-14
COMPUTERISED MEASUREMENT BOOK MEASURMENT & ABSTRACT OF COST 9th R.A. Bill
C.M.B NO: 267/EE/MPD
CERTIFICATE
izekf.kr fd;k tkrk gS fd bl dEI;wVj eki cgh esa 1 ls 38 rd 38 dqy i`"B gS A leLr iq"B Øekuqlkj gSA
Executive Engineer
Mussoorie Project Division
CPWD, Mussoorie.

## Review Notes
REVIEW NOTES
BY SUPERIOR OFFICER OF THE DEPARTMENT
Date | Pages Recording measurements subjected to test check | Value of measurement checked | Results of check excercised | Dated initials and designation of the checking officers

## Measurment
Page-2
MEASUREMENT SHEETS
Name of work: Construction of Studio Apartment at Cozy Cot at LBSNAA,Mussoorie. (EFC Scheme No.12 A of 12th Five Year Plan).
Name of Contractor: Anil Dutt Sharma
Agmt. No. : 36/EE/MPD/2013-14 |  |  |  |  | Sl no. of this bill : 9TH R.A. bill
Date of Measurements :- 12.-03-2015
Item No | Particulars | Particulars |  |  |  |  | Contents or Area
|  | Nos |  | L | B | D
1 | Earth work in excavation by mechanical means (Hydraulic excavator )/ manual means over areas (exceeding 30cm in depth. 1.5m in width as well as 10 sqm on plan) including disposal of excavated earth, lead upto 50m and lift upto 1.5m, disposed earth to be levelled and neatly dressed.
1.1 | All kinds of soil
|  | 1 | 1 | 16 | 3.36 | 1.47 | 79.03 | cum
|  | 1 | 1 | 16 | 0.7 | 0.65 | 7.28
Total
| Total Quantity= | [5 empty] | 86.31 | cum
| Less already measured vide CMB-256 P-32 | [5 empty] | -81.18
[7 empty] | 5.13 | cum
C/o on P- 20 / TCMB-267
Page-3
MEASUREMENT SHEETS
Name of work: Construction of Studio Apartment at Cozy Cot at LBSNAA,Mussoorie. (EFC Scheme No.12 A of 12th Five Year Plan).
Name of Contractor: Anil Dutt Sharma
Agmt. No. : 36/EE/MPD/2013-14 |  |  |  |  | Sl no. of this bill : 9TH R.A. bill
Date of Measurements :- 12-05-2015
Item No | Particulars | Particulars |  |  |  |  | Contents or Area
|  | Nos |  | L | B | D
8 | Providing and laying in position cement concrete of specified grade excluding the cost of centring and shuttering - All work upto plinth level :
8.2 | 1:5:10 (1 cement : 5 coarse sand : 10 graded stone aggregate 40 mm nominal size)
|  | 1 | 1 | 16 | 3.36 | 0.1 | 5.38 | cum
Total
| Total Quantity= | [5 empty] | 5.38 | cum
| Less already measured vide CMB-256 P-33 | [5 empty] | -5.06
[7 empty] | 0.32 | cum
C/o on P- 20 / TCMB-267
Page-4
MEASUREMENT SHEETS
Name of work: Construction of Studio Apartment at Cozy Cot at LBSNAA,Mussoorie. (EFC Scheme No.12 A of 12th Five Year Plan).
Name of Contractor: Anil Dutt Sharma
Agmt. No. : 36/EE/MPD/2013-14 |  |  |  |  | Sl no. of this bill : 9TH R.A. bill
Date of Measurements :- 12-05-2015
Item No | Particulars | Particulars |  |  |  |  | Contents or Area
|  | Nos |  | L | B | D
125 | Providing and applying two component cementitious acrylic flexible water proofing coating with Brush bond RFX of FOSROC / PIDIFIN 2K of pidilite / Master seal 550EL of BASF includingembeding polypropylene fibre matt having weight 50gms per sqm in between first and second coating of treatment including cleaning the surface all lifts and lead etc complete. Application of two component system shall be done as per manufacture's specification, recommendation and as per direction of Engineer-In-Charge.
Water proofing in top most type-II Qtr.
| In bathroom | 4 | 1 | 1.68 | 2.4 |  | 16.13 | sqm
|  | 4 | 2 | 0.25 | 2.27 |  | 4.54
|  | 4 | 2 | 0.25 | 1.4 |  | 2.8
| Kitchen | 4 | 2 | 2.27 | 0.25 |  | 4.54
|  | 4 | 2 | 1.58 | 0.25 |  | 3.16
|  | 4 | 1 | 2.4 | 1.83 |  | 17.57
Total
| Total Quantity= | [5 empty] | 48.74 | sqm
C/o on P- 22 / TCMB-267
Page-5
MEASUREMENT SHEETS
Name of work: Construction of Studio Apartment at Cozy Cot at LBSNAA,Mussoorie. (EFC Scheme No.12 A of 12th Five Year Plan).
Name of Contractor: Anil Dutt Sharma
Agmt. No. : 36/EE/MPD/2013-14 |  |  |  |  | Sl no. of this bill : 9TH R.A. bill
Date of Measurements :- 12-03-2015
Item No | Particulars | Particulars |  |  |  |  | Contents or Area
|  | Nos |  | L | B | D
EIS-1/5 | 12 mm cement plaster finished with a floating coat of neat cement of mix :
1:4 (1 cement: 4 Coarse sand)
| In bathroom | 4 | 1 | 1.68 | 2.4 |  | 16.13 | sqm
|  | 4 | 2 | 0.25 | 2.27 |  | 4.54
|  | 4 | 2 | 0.25 | 1.4 |  | 2.8
| Kitchen | 4 | 2 | 2.27 | 0.25 |  | 4.54
|  | 4 | 2 | 1.58 | 0.25 |  | 3.16
|  | 4 | 1 | 2.4 | 1.83 |  | 17.57
| Total Quantity= | [5 empty] | 48.74 | sqm
C/o on P- 22 / TCMB-267
Page-7
MEASUREMENT SHEETS
Name of work: Construction of Studio Apartment at Cozy Cot at LBSNAA,Mussoorie. (EFC Scheme No.12 A of 12th Five Year Plan).
Name of Contractor: Anil Dutt Sharma
Agmt. No. : 36/EE/MPD/2013-14 |  |  |  |  | Sl no. of this bill : 9TH R.A. bill
Date of Measurements :- 25-03-2015
Item No | Particulars | Particulars |  |  |  |  | Contents or Area
|  | Nos |  | L | B | D
10 | Providing and laying in position machine batched and machine mixed design mix M-25 grade cement concrete for reinforced cement concrete work, using cement content as per approved design mix, including pumping of concrete to site of laying but excluding the cost of centering, shuttering, finishing and reinforcement, including admixtures in recommended proportions as per IS: 9103 to accelerate, retard setting of concrete, improve workability without impairing strength and durability as per direction of Engineer-in-charge (Note :- Cement content considered in this item is @ 330 kg/cum. Excess/less cement used as per design mix is payable/recoverable separately).
10.1 | All works upto plinth level.
| RCC wall base | 1 | 1 | 15.4 | 2.9 | 0.6 | 26.8 | sqm
|  | 1 | 1 | 15.4 | 0.6 | 0.7 | 6.47
| Total Quantity= | [5 empty] | 33.27 | sqm
C/o on P- 20 / TCMB-267
Page-8
MEASUREMENT SHEETS
Name of work: Construction of Studio Apartment at Cozy Cot at LBSNAA,Mussoorie. (EFC Scheme No.12 A of 12th Five Year Plan).
Name of Contractor: Anil Dutt Sharma
Agmt. No. : 36/EE/MPD/2013-14 |  |  |  |  | Sl no. of this bill : 9TH R.A. bill
Date of Measurements :- 25-03-2015
Item No | Particulars | Particulars |  |  |  |  | Contents or Area
|  | Nos |  | L | B | D
11 | Centring and shuttering including strutting, propping etc. and removal of form for :
11.1 | Foundations, footings, bases of columns, etc. for mass concrete.
|  | 1 | 2 | 15.4 | 0.6 |  | 18.48 | sqm
|  | 1 | 2 | 2.9 | 0.6 |  | 3.48
|  | 1 | 2 | 0.7 | 0.6 |  | 0.84
| Total Quantity= | [5 empty] | 22.8 | sqm
C/o on P- 20 / TCMB-267
Page-12
MEASUREMENT SHEETS
Name of work: Construction of Studio Apartment at Cozy Cot at LBSNAA,Mussoorie. (EFC Scheme No.12 A of 12th Five Year Plan).
Name of Contractor: Anil Dutt Sharma
Agmt. No. : 36/EE/MPD/2013-14 |  |  |  |  | Sl no. of this bill : 9TH R.A. bill
Date of Measurements :- 25-03-2015
Item No | Particulars | Particulars |  |  |  |  | Contents or Area
|  | Nos |  | L | B | D
14 | Brick work with common burnt clay F.P.S. (non modular) bricks of class designation 7.5 in superstructure above plinth level up to floor V level in all shapes and sizes in :
14.1 | Cement mortar 1:6 (1 cement : 6 coarse sand)
| For Glazed window | 2 | 6 | 3.04 | 0.23 | 0.92 | 7.72 | cum
| Above tie beam | 1 | 2 | 6.91 | 0.23 | 3.4 | 10.81
| Column | 2 | 4 | 0.23 | 0.23 | 3.4 | 1.44
| Total Quantity= | [5 empty] | 19.97 | cum
C/o on P- 21 / TCMB-267
Page-13
MEASUREMENT SHEETS
Name of work: Construction of Studio Apartment at Cozy Cot at LBSNAA,Mussoorie. (EFC Scheme No.12 A of 12th Five Year Plan).
Name of Contractor: Anil Dutt Sharma
Agmt. No. : 36/EE/MPD/2013-14 |  |  |  |  | Sl no. of this bill : 9TH R.A. bill
Date of Measurements :- 25-03-2015
Item No | Particulars | Particulars |  |  |  |  | Contents or Area
|  | Nos |  | L | B | D
47 | Providing and fixing soil, waste and vent pipes :
47.1 | 100 mm dia.
47.1.1 | Centrifugally cast (spun) iron socket & spigot (S&S) pipe as per IS: 3989.
|  | 4 | 3 | 2.51 |  |  | 30.12 | mtr
|  | 4 | 3 | 2.71 |  |  | 32.52
|  | 4 | 3 | 2.71 |  |  | 32.52
|  | 2 | 3 | 3 |  |  | 18
|  | 2 | 3 | 2.71 |  |  | 16.26
| Total Quantity= | [5 empty] | 129.42 | mtr
C/o on P- 21 / TCMB-267
Date of Measurements :- 25-03-2015
Item No | Particulars | Particulars |  |  |  |  | Contents or Area
|  | Nos |  | L | B | D
56 | Providing lead caulked joints to sand cast iron/ centrifugally cast (spun) iron pipes and fittings of diameter:
56.1 | 100 mm
|  | 12 | 6 |  |  |  | 72 | each
| Total Quantity= | [5 empty] | 72 | each
C/o on P- 21 / TCMB-267
Page-14
MEASUREMENT SHEETS
Name of work: Construction of Studio Apartment at Cozy Cot at LBSNAA,Mussoorie. (EFC Scheme No.12 A of 12th Five Year Plan).
Name of Contractor: Anil Dutt Sharma
Agmt. No. : 36/EE/MPD/2013-14 |  |  |  |  | Sl no. of this bill : 9TH R.A. bill
Date of Measurements :- 25-03-2015
Item No | Particulars | Particulars |  |  |  |  | Contents or Area
|  | Nos |  | L | B | D
59 | Providing and fixing G.I. pipes complete with G.I. fittings and clamps including making good the walls etc. concealed pipe including painting with anti corrosive bitumastic paint, cutting chases and making good the wall.
59.1 | 15 mm dia nominal bore
Pipe connected to 20 mm pipe
| (0.35 + 0.07) = 0.42 | 4 | 2 | 0.42 |  |  | 3.36 | mtr
| (0.38+0.10) = 0.48 | 2 | 2 | 0.48 |  |  | 1.92
| (0.45 + 0.10) = 0.55 | 2 | 2 | 0.55 |  |  | 2.2
| Total Quantity= | [5 empty] | 7.48 | mtr
C/o on P- 21 / TCMB-267
Page-15
MEASUREMENT SHEETS
Name of work: Construction of Studio Apartment at Cozy Cot at LBSNAA,Mussoorie. (EFC Scheme No.12 A of 12th Five Year Plan).
Name of Contractor: Anil Dutt Sharma
Agmt. No. : 36/EE/MPD/2013-14 |  |  |  |  | Sl no. of this bill : 9TH R.A. bill
Date of Measurements :- 25-03-2015
Item No | Particulars | Particulars |  |  |  |  | Contents or Area
|  | Nos |  | L | B | D
58 | Providing and fixing G.I. pipes complete with G.I. fittings and clamps, including cutting and making good the walls etc. Internal work - Exposed on wall
58.1 | 20 mm dia. nominal bore
Right stacks
|  | 4 | 1 | 6 |  |  | 24 | mtr
|  | 1 | 1 | 7.6 |  |  | 7.6
|  | 1 | 1 | 7.65 |  |  | 7.65
|  | 1 | 1 | 7.7 |  |  | 7.7
|  | 1 | 1 | 7.75 |  |  | 7.75
|  | 1 | 1 | 0.45 |  |  | 0.45
|  | 1 | 1 | 2.7 |  |  | 2.7
|  | 1 | 1 | 5.7 |  |  | 5.7
|  | 1 | 1 | 8.72 |  |  | 8.72
|  | 1 | 1 | 11.72 |  |  | 11.72
| Lt Stack | 4 | 1 | 6 |  |  | 24
|  | 1 | 1 | 5.71 |  |  | 5.71
|  | 1 | 1 | 5.81 |  |  | 5.81
|  | 1 | 1 | 5.92 |  |  | 5.92
|  | 1 | 1 | 6 |  |  | 6
|  | 1 | 1 | 0.45 |  |  | 0.45
|  | 1 | 1 | 2.7 |  |  | 2.7
|  | 1 | 1 | 5.7 |  |  | 5.7
|  | 1 | 1 | 8.72 |  |  | 8.72
|  | 1 | 1 | 11.72 |  |  | 11.72
| Total Quantity= | [5 empty] | 160.72 | mtr
C/o on P- 21 / TCMB-267
Page-16
MEASUREMENT SHEETS
Name of work: Construction of Studio Apartment at Cozy Cot at LBSNAA,Mussoorie. (EFC Scheme No.12 A of 12th Five Year Plan).
Name of Contractor: Anil Dutt Sharma
Agmt. No. : 36/EE/MPD/2013-14 |  |  |  |  | Sl no. of this bill : 9TH R.A. bill
Date of Measurements :- 25-03-2015
Item No | Particulars | Particulars |  |  |  |  | Contents or Area
|  | Nos |  | L | B | D
65 | Providing and fixing G.I. Union in existing G.I. pipe line, cutting and threading the pipe and making long screws including excavation, refilling the earth or cutting of wall and making good the same complete wherever required :
65.1 | 15 mm nominal bore.
|  | 8 | 2 |  |  |  | 16 | each
| Total Quantity= | [5 empty] | 16 | each
C/o on P- 21 / TCMB-267
Page-17
MEASUREMENT SHEETS
Name of work: Construction of Studio Apartment at Cozy Cot at LBSNAA,Mussoorie. (EFC Scheme No.12 A of 12th Five Year Plan).
Name of Contractor: Anil Dutt Sharma
Agmt. No. : 36/EE/MPD/2013-14 |  |  |  |  | Sl no. of this bill : 9TH R.A. bill
Date of Measurements :- 25-03-2015
Item No | Particulars | Particulars |  |  |  |  | Contents or Area
|  | Nos |  | L | B | D
EIS-1/7 | Providing and fixing aluminium sub frame work for windows and ventilators with extruded built up standard tubular sections of approved make conforming to IS: 733 and IS: 1285, fixed with dash fastener of required dia and size (Dash fastener to be paid for separately).
Sub frame for Type-II
| Lounge | 8 | 2 | 1.855 |  | 29.68 |  | mtr
|  | 8 | 2 | 1.25 |  | 20
| Drawing room | 8 | 2 | 1.535 |  | 24.56
|  | 8 | 2 | 1.25 |  | 20
| Kitchen | 8 | 2 | 1.17 |  | 18.72
|  | 8 | 2 | 1.025 |  | 16.4
| Toilet | 8 | 2 | 0.66 |  | 10.56
|  | 8 | 2 | 0.99 |  | 15.84
| Bedroom | 8 | 2 | 1.25 |  | 20
|  | 8 | 2 | 1.22 |  | 19.52
| Window to open area | 8 | 2 | 1.26 |  | 20.16
|  | 8 | 2 | 1.26 |  | 20.16
| Type-III lounge | 7 | 2 | 1.85 |  | 25.9
|  | 7 | 2 | 1.26 |  | 17.64
| Drawing room | 7 | 2 | 1.56 |  | 21.84
|  | 7 | 2 | 1.31 |  | 18.34
| Kitchen | 7 | 2 | 1.17 |  | 16.38
|  | 7 | 2 | 1.025 |  | 14.35
| Toilet | 7 | 2 | 0.66 |  | 9.24
|  | 7 | 2 | 0.99 |  | 13.86
| Study room | 7 | 2 | 1.23 |  | 17.22
|  | 7 | 2 | 1.3 |  | 18.2
|  | 7 | 2 | 1.55 |  | 21.7
|  | 7 | 2 | 1.22 |  | 17.08
|  | 7 | 2 | 0.94 |  | 13.16
|  | 7 | 2 | 1.23 |  | 17.22
477.73
| Weight @ P-1 /TCMB |  |  |  | @ | 1.565 | 747.65
| Total Quantity= | [5 empty] | 747.65 | kg
C/o on P- 22 / TCMB-267
Page-18
MEASUREMENT SHEETS
Name of work: Construction of Studio Apartment at Cozy Cot at LBSNAA,Mussoorie. (EFC Scheme No.12 A of 12th Five Year Plan).
Name of Contractor: Anil Dutt Sharma
Agmt. No. : 36/EE/MPD/2013-14 |  |  |  |  | Sl no. of this bill : 9TH R.A. bill
Date of Measurements :- 25-03-2015
Item No | Particulars | Particulars |  |  |  |  | Contents or Area
|  | Nos |  | L | B | D
EIS-1/1 | Add for using extra cement in the items of design mix over and above the specified cement content therein.
| Brought from CMB-256 P-19 | [5 empty] | 3.33 | Cum
| Brought from CMB-256 P-20 | [5 empty] | 8.07 | Cum
| Brought from TCMB- P- | [5 empty] | 33.27 | Cum
44.67
[6 empty] | @ | 0.48
21.44
| Total Quantity= | [5 empty] | 21.44 | Qtl
C/o on P- 22 / TCMB-267
Page-19
MEASUREMENT SHEETS
Name of work: Construction of Studio Apartment at Cozy Cot at LBSNAA,Mussoorie. (EFC Scheme No.12 A of 12th Five Year Plan).
Name of Contractor: Anil Dutt Sharma
Agmt. No. : 36/EE/MPD/2013-14 |  |  |  |  | Sl no. of this bill : 9TH R.A. bill
Date of Measurements :- 25-03-2015
Item No | Particulars | Particulars |  |  |  |  | Contents or Area
|  | Nos |  | L | B | D
Measuremen for Secured Advance
1 | Vetrified tile 600 x 600 | 100 | 4 | 0.6 | 0.6 |  | 144 | sqm
|  | 100 | 4 | 0.6 | 0.6 |  | 144
|  | 100 | 4 | 0.6 | 0.6 |  | 144
|  | 100 | 4 | 0.6 | 0.6 |  | 144
|  | 100 | 4 | 0.6 | 0.6 |  | 144
|  | 100 | 4 | 0.6 | 0.6 |  | 144
|  | 75 | 4 | 0.6 | 0.6 |  | 108
[7 empty] | 972 | sqm
2 | Wall tile 300 x 600 | 100 | 5 | 0.3 | 0.6 |  | 90
|  | 100 | 5 | 0.3 | 0.6 |  | 90
|  | 100 | 5 | 0.3 | 0.6 |  | 90
|  | 100 | 5 | 0.3 | 0.6 |  | 90
|  | 100 | 5 | 0.3 | 0.6 |  | 90
|  | 80 | 5 | 0.3 | 0.6 |  | 72
[7 empty] | 522 | sqm
C/o on P- / TCMB-

## Cozymeasurement
Page-1
MEASUREMENT SHEETS
Name of work: Construction of Studio Apartment at Cozy Cot at LBSNAA,Mussoorie. (EFC Scheme No.12 A of 12th Five Year Plan).
Name of Contractor: Anil Dutt Sharma
Agmt. No. : 36/EE/MPD/2013-14 | [10 empty] | Sl no. of this bill : 9TH R.A. bill
Date of Measurement : 12.03-2015
Record of Actual Weight of Sample (For record only)
| Sample | [6 empty] | Length (Metre) | Weight (kg ) | Weight (kg/m) | Avg. Weight (kg/m) | Standard Weight (Kq/m) | Weight allowed (Kg/m)
(A) | Sub frame 3 mm thick
| (0.61 +0.66)/2 = 0.635 | [6 empty] | 0.635 | 0.994 | 1.565 | 1.565 | - | 1.565
(B) | 40 x 40 Pipe hollow tube
[8 empty] | 0.552 | 2.38 | 4.312 | 4.312 | - | 4.312
(B) | 60 x 60 Pipe hollow tube
[8 empty] | 1.005 | 5.306 | 5.28 | 5.28 | - | 5.28
Not for payment
Page-6
MEASUREMENT SHEETS
Name of work: Construction of Studio Apartment at Cozy Cot at LBSNAA,Mussoorie. (EFC Scheme No.12 A of 12th Five Year Plan).
Name of Contractor: Anil Dutt Sharma
Agmt. No. : 36/EE/MPD/2013-14 | [10 empty] | Sl no. of this bill : 9TH R.A. bill
Date of Measurement : 16-03-2015
Item No | Particulars | Dia in mm |  | Nos |  |  | L |  |  |  | Total length (meter) |  |  |  | Weight
[9 empty] | 8Ø | 10Ø | 12Ø | 16Ø | 20Ø | 25Ø
12 | Steel reinforcement for R.C.C. work including straightening, cutting, bending, placing in position and binding all complete.
12.1 | Thermo-Mechanically Treated bars.in foundation upto plinth level.
| RCC wall base | [7 empty] | 8Ø | 10Ø | 12Ø | 16Ø | 20Ø | 25Ø
| Top | 16 | Ø | 1 | x | 87 | 3.6 |  | — | — | — | 313.2 | — | —
| Bottom | 16 | Ø | 1 | x | 104 | 3.6 |  | — | — | — | 374.4 | — | —
| Binder | 8 | Ø | 1 | x | 29 | 16 |  | 464 | — | — | — | — | —
| Top | 8 | Ø | 1 | x | 29 | 16 |  | 464 | — | — | — | — | —
| Overlap | 8 | Ø | 2 | x | 29 | 0.4 |  | 23.2 | — | — | — | — | —
| Chair | 16 | Ø | 2 | x | 14 | 2.05 |  | — | — | — | 57.4 | — | —
| Binder in key | 8 | Ø | 2 | x | 7 | 16 |  | 224 | — | — | — | — | —
| Overlap | 8 | Ø | 2 | x | 7 | 0.4 |  | 5.6 | — | — | — | — | —
| Binder | 16 | Ø | 1 | x | 1 | 16 |  | — | — | — | 16 | — | —
| Overlap | 16 | Ø | 1 | x | 1 | 0.8 |  | — | — | — | 0.8 | — | —
| Wall steel | 16 | Ø | 1 | x | 62 | 4.8 |  | — | — | — | 297.6 | — | —
|  | 25 | Ø | 1 | x | 52 | 4.8 |  | — | — | — | — | — | 249.6
|  | 25 | Ø | 1 | x | 52 | 3.14 |  | — | — | — | — | — | 163.28
| Walll binder | 10 | Ø | 1 | x | 20 | 15.42 |  | — | 308.4 | — | — | — | —
| Overlap | 10 | Ø | 1 | x | 20 | 0.5 |  | — | 10 | — | — | — | —
| Binder | 8 | Ø | 1 | x | 30 | 15.42 |  | 462.6 | — | — | — | — | —
| Overlap | 8 | Ø | 1 | x | 30 | 0.4 |  | 12 | — | — | — | — | —
| Beam for glazed window T/B | 16 | Ø | 6 | x | 6 | 7 |  | — | — | — | 252 | — | —
| Ring | 8 | Ø | 6 | x | 67 | 1.2 |  | 482.4 | — | — | — | — | —
| Shorter beam T/B | 16 | Ø | 2 | x | 3 | 3.81 |  | — | — | — | 22.86 | — | —
| Rings | 8 | Ø | 1 | x | 30 | 1.2 |  | 36 | — | — | — | — | —
| U | 12 | Ø | 2 | x | 13 | 1.5 |  | — | — | 39 | — | — | —
[7 empty] | Total |  | 2173.8 | 318.4 | 39 | 1334.26 | 0 | 412.88
| Unit Weight kg/m As per P-12 /CMB-238 | [7 empty] | 0.395 | 0.617 | 0.888 | 1.58 | 2.47 | 3.85
| Weight | [7 empty] | 858.65 | 196.45 | 34.63 | 2108.13 | 0 | 1589.59 | 4787.45
[13 empty] | Total |  | 4787.45 | Kg
C/O on P- 20 /TCMB-267
Page-9
MEASUREMENT SHEETS
Name of work: Construction of Studio Apartment at Cozy Cot at LBSNAA,Mussoorie. (EFC Scheme No.12 A of 12th Five Year Plan).
Name of Contractor: Anil Dutt Sharma
Agmt. No. : 36/EE/MPD/2013-14 | [10 empty] | Sl no. of this bill : 9TH R.A. bill
Date of Measurement : 25-03-2015
Item No | Particulars | Dia in mm |  | Nos |  |  | L |  |  |  | Total length (meter) |  |  |  | Weight
[11 empty] | 50 x 50 x6 | 40x40x5
26 | Steel work in built up tubular ( round, square or rectangular hollow tubes etc.) trusses etc. including cutting, hoisting, fixing in position and applying a priming coat of approved steel primer, including welding and bolted with special shaped washers etc. complete.
26.1 | Hot finished welded type tubes
[12 empty] | 40 x 40 | 60x60
| Pipe for ceiling bedroom | 60 | Ø | 2 | x | 4 | 4 |  | — | — | — | — | 32 | —
|  | 60 | Ø | 2 | x | 4 | 2.74 |  | — | — | — | — | 21.92 | —
|  | 60 | Ø | 4 | x | 4 | 3.87 |  | — | — | — | — | 61.92 | —
|  | 60 | Ø | 4 | x | 10 | 0.55 |  | — | — | — | — | 22 | —
|  | 60 | Ø | 4 | x | 3 | 0.51 |  | — | — | — | — | 6.12 | —
|  | 60 | Ø | 4 | x | 4 | 0.35 |  | — | — | — | — | 5.6 | —
|  | 60 | Ø | 4 | x | 1 | 0.36 |  | — | — | — | — | 1.44 | —
| Pipe for balcony | 60 | Ø | 4 | x | 2 | 2.87 |  | — | — | — | — | 22.96 | —
|  | 60 | Ø | 4 | x | 2 | 0.89 |  | — | — | — | — | 7.12 | —
|  | 60 | Ø | 4 | x | 1 | 2.75 |  | — | — | — | — | 11 | —
|  | 60 | Ø | 4 | x | 2 | 0.52 |  | — | — | — | — | 4.16 | —
|  | 60 | Ø | 2 | x | 4 | 0.3 |  | — | — | — | — | 2.4 | —
| Toilet and kitchen floor | 60 | Ø | 4 | x | 3 | 1.3 |  | — | — | — | — | 15.6 | —
|  | 60 | Ø | 4 | x | 2 | 1 |  | — | — | — | — | 8 | —
|  | 60 | Ø | 4 | x | 1 | 0.52 |  | — | — | — | — | 2.08 | —
|  | 60 | Ø | 4 | x | 1 | 0.29 |  | — | — | — | — | 1.16 | —
|  | 60 | Ø | 4 | x | 2 | 1.62 |  | — | — | — | — | 12.96 | —
|  | 60 | Ø | 4 | x | 1 | 1.5 |  | — | — | — | — | 6 | —
|  | 60 | Ø | 4 | x | 2 | 0.86 |  | — | — | — | — | 6.88 | —
|  | 60 | Ø | 4 | x | 1 | 0.52 |  | — | — | — | — | 2.08 | —
|  | 60 | Ø | 4 | x | 1 | 0.29 |  | — | — | — | — | 1.16 | —
| Bathroom | 60 | Ø | 4 | x | 2 | 2.17 |  | — | — | — | — | 17.36 | —
|  | 60 | Ø | 4 | x | 2 | 1.29 |  | — | — | — | — | 10.32 | —
|  | 60 | Ø | 4 | x | 2 | 2.04 |  | — | — | — | — | 16.32 | —
|  | 60 | Ø | 4 | x | 1 | 0.52 |  | — | — | — | — | 2.08 | —
|  | 60 | Ø | 4 | x | 1 | 0.55 |  | — | — | — | — | 2.2 | —
|  | 60 | Ø | 4 | x | 1 | 0.1 |  | — | — | — | — | 0.4 | —
| Kitchen | 60 | Ø | 4 | x | 2 | 2.18 |  | — | — | — | — | 17.44 | —
|  | 60 | Ø | 4 | x | 2 | 1.53 |  | — | — | — | — | 12.24 | —
|  | 60 | Ø | 4 | x | 2 | 2.04 |  | — | — | — | — | 16.32 | —
|  | 60 | Ø | 4 | x | 1 | 0.52 |  | — | — | — | — | 2.08 | —
|  | 60 | Ø | 4 | x | 1 | 0.55 |  | — | — | — | — | 2.2 | —
|  | 60 | Ø | 4 | x | 1 | 0.33 |  | — | — | — | — | 1.32 | —
|  | 60 | Ø | 4 | x | 2 | 3.44 |  | — | — | — | — | 27.52 | —
|  | 60 | Ø | 4 | x | 2 | 2.75 |  | — | — | — | — | 22 | —
|  | 60 | Ø | 4 | x | 4 | 3.28 |  | — | — | — | — | 52.48 | —
|  | 60 | Ø | 4 | x | 6 | 0.55 |  | — | — | — | — | 13.2 | —
|  | 60 | Ø | 4 | x | 2 | 0.52 |  | — | — | — | — | 4.16 | —
|  | 60 | Ø | 4 | x | 2 | 0.34 |  | — | — | — | — | 2.72 | —
| Lounge | 60 | Ø | 4 | x | 1 | 3.46 |  | — | — | — | — | 13.84 | —
|  | 60 | Ø | 4 | x | 1 | 2.18 |  | — | — | — | — | 8.72 | —
|  | 60 | Ø | 4 | x | 2 | 0.27 |  | — | — | — | — | 2.16 | —
|  | 60 | Ø | 4 | x | 1 | 0.32 |  | — | — | — | — | 1.28 | —
|  | 60 | Ø | 4 | x | 1 | 0.96 |  | — | — | — | — | 3.84 | —
|  | 60 | Ø | 4 | x | 6 | 3.12 |  | — | — | — | — | 74.88 | —
[8 empty] | C/O | 0 | 0 | 0 | 0 | 581.64 | 0
Page-10
MEASUREMENT SHEETS
Name of work: Construction of Studio Apartment at Cozy Cot at LBSNAA,Mussoorie. (EFC Scheme No.12 A of 12th Five Year Plan).
Name of Contractor: Anil Dutt Sharma
Agmt. No. : 36/EE/MPD/2013-14 | [10 empty] | Sl no. of this bill : 9TH R.A. bill
Date of Measurement : 25-03-2015
Item No | Particulars | Dia in mm |  | Nos |  |  | L |  |  |  | Total length (meter) |  |  |  | Weight
[11 empty] | 50 x 50 x6 | 40x40x5
26 | Steel work in built up tubular ( round, square or rectangular hollow tubes etc.) trusses etc. including cutting, hoisting, fixing in position and applying a priming coat of approved steel primer, including welding and bolted with special shaped washers etc. complete.
26.1 | Hot finished welded type tubes
[12 empty] | 40 x 40 | 60x60
[8 empty] | B/F | 0 | 0 | 0 | 0 | 581.64 | 0
|  | 60 | Ø | 4 | x | 1 | 2.86 |  | — | — | — | — | 11.44 | —
|  | 60 | Ø | 4 | x | 2 | 0.3 |  | — | — | — | — | 2.4 | —
|  | 60 | Ø | 4 | x | 8 | 0.55 |  | — | — | — | — | 17.6 | —
|  | 60 | Ø | 4 | x | 2 | 0.52 |  | — | — | — | — | 4.16 | —
| Pipe for canopy Top pipe | 60 | Ø | 2 | x | 1 | 2.3 |  | — | — | — | — | 4.6 | —
|  | 60 | Ø | 2 | x | 1 | 2.32 |  | — | — | — | — | 4.64 | —
| (V) | 60 | Ø | 2 | x | 1 | 0.25 |  | — | — | — | — | 0.5 | —
|  | 60 | Ø | 2 | x | 1 | 0.23 |  | — | — | — | — | 0.46 | —
|  | 60 | Ø | 2 | x | 1 | 0.3 |  | — | — | — | — | 0.6 | —
|  | 60 | Ø | 2 | x | 1 | 0.36 |  | — | — | — | — | 0.72 | —
|  | 60 | Ø | 2 | x | 1 | 0.38 |  | — | — | — | — | 0.76 | —
| Horizontal truss | 60 | Ø | 2 | x | 2 | 1.89 |  | — | — | — | — | 7.56 | —
|  | 60 | Ø | 2 | x | 2 | 1.38 |  | — | — | — | — | 5.52 | —
|  | 60 | Ø | 2 | x | 2 | 0.3 |  | — | — | — | — | 1.2 | —
|  | 60 | Ø | 2 | x | 4 | 0.24 |  | — | — | — | — | 1.92 | —
|  | 60 | Ø | 2 | x | 1 | 0.25 |  | — | — | — | — | 0.5 | —
| Purline | 60 | Ø | 1 | x | 6 | 2.52 |  | — | — | — | — | 15.12 | —
| Pipe for partition above tie beam | 40 | Ø | 1 | x | 1 | 3.1 |  | — | — | — | 3.1 | — | —
|  | 40 | Ø | 1 | x | 1 | 3.05 |  | — | — | — | 3.05 | — | —
|  | 40 | Ø | 1 | x | 1 | 2.87 |  | — | — | — | 2.87 | — | —
|  | 40 | Ø | 1 | x | 1 | 2.75 |  | — | — | — | 2.75 | — | —
|  | 40 | Ø | 1 | x | 1 | 2.59 |  | — | — | — | 2.59 | — | —
|  | 40 | Ø | 1 | x | 1 | 2.44 |  | — | — | — | 2.44 | — | —
|  | 40 | Ø | 1 | x | 1 | 2.24 |  | — | — | — | 2.24 | — | —
|  | 40 | Ø | 1 | x | 1 | 2.08 |  | — | — | — | 2.08 | — | —
| (H) | 40 | Ø | 1 | x | 1 | 4.03 |  | — | — | — | 4.03 | — | —
|  | 40 | Ø | 1 | x | 1 | 0.54 |  | — | — | — | 0.54 | — | —
|  | 40 | Ø | 1 | x | 1 | 0.56 |  | — | — | — | 0.56 | — | —
|  | 40 | Ø | 1 | x | 5 | 0.57 |  | — | — | — | 2.85 | — | —
|  | 40 | Ø | 1 | x | 3 | 0.34 |  | — | — | — | 1.02 | — | —
|  | 40 | Ø | 1 | x | 4 | 0.57 |  | — | — | — | 2.28 | — | —
|  | 40 | Ø | 1 | x | 3 | 0.59 |  | — | — | — | 1.77 | — | —
|  | 40 | Ø | 1 | x | 1 | 0.58 |  | — | — | — | 0.58 | — | —
|  | 40 | Ø | 1 | x | 1 | 0.38 |  | — | — | — | 0.38 | — | —
[7 empty] | Total |  | 0 | 0 | 0 | 35.13 | 661.34 | 0
| Weight P-1 /TCMB | [10 empty] | 4.312 | 5.28
| Weight | [7 empty] | 0 | 0 | 0 | 151.48 | 3491.88 | 0 | 3643.36
[13 empty] | Total |  | 3643.36 | Kg
C/O on P- 21 /TCMB-267
Page-11
MEASUREMENT SHEETS
Name of work: Construction of Studio Apartment at Cozy Cot at LBSNAA,Mussoorie. (EFC Scheme No.12 A of 12th Five Year Plan).
Name of Contractor: Anil Dutt Sharma
Agmt. No. : 36/EE/MPD/2013-14 | [10 empty] | Sl no. of this bill : 9TH R.A. bill
Date of Measurement : 25-03-2015
Item No | Particulars | Dia in mm |  | Nos |  |  | L |  |  |  | Total length (meter) |  |  |  | Weight
[9 empty] | 12mm | 10mm | 50 x 50 x6 | 40x40x5
29 | Steel work welded in built up sections/ framed work including cutting, hoisting, fixing in position and applying a priming coat of approved steel primer using structural steel etc. as required.
29.1 | In gratings, frames, guard bar, ladder, railings, brackets, gates and similar works.
[9 empty] | 12mm | 10mm | 8mm | 50 x 50 x6 | 40x40x6
| Angle 50 x 50 x 6 | 50 | Ø | 1 | x | 8 | 0.13 |  | — | — | — | 1.04 | — | —
|  | 50 | Ø | 1 | x | 4 | 0.5 |  | — | — | — | 2 | — | —
|  | 50 | Ø | 1 | x | 8 | 0.05 |  | — | — | — | 0.4 | — | —
| 8 mm Plate | 8 | Ø | 1 | x | 0.5 | 0.15 | 0.15 | — | — | 0.01 | — | — | —
[7 empty] | Total |  | 0 | 0 | 0.01 | 3.44 | 0 | 0
| Unit Weight kg/m As per P-12 /CMB-238 and CMB-256 P-2 | [7 empty] | 94 | 78.43 | 62.74 | 4.42 | 3.41
| Weight | [7 empty] | 0 | 0 | 0.63 | 15.2 | 0 | 0 | 15.83
[13 empty] | Total |  | 15.83 | Kg
C/O on P- 21 /TCMB-267

## Abstract of Qty
Abstract of Quantity (9th RA Bill)
Name of work: Construction of Studio Apartment at Cozy Cot at LBSNAA,Mussoorie. (EFC Scheme No.12 A of 12th Five Year Plan).
Name of Contractor: Anil Dutt Sharma
Agmt. No. : 36/EE/MPD/2013-14
Date of start : 03-10-2013
Date of Completion : Work is in Progress
Date of Abstract : 11-03-2015 |  | Situation : Mussoorie
Agmt item No. | Description | Unit | Qty.
A | B | C | D
1 | Earth work in excavation by mechanical means (Hydraulic excavator )/ manual means over areas (exceeding 30cm in depth. 1.5m in width as well as 10 sqm on plan) including disposal of excavated earth, lead upto 50m and lift upto 1.5m, disposed earth to be levelled and neatly dressed.
1.1 | All kinds of soil
| B/F Page- 2 /TCMB | cum | 5.13
| C/O Page- 23 /TCMB | cum | 5.13
8 | Providing and laying in position cement concrete of specified grade excluding the cost of centring and shuttering - All work upto plinth level :
8.2 | 1:5:10 (1 cement : 5 coarse sand : 10 graded stone aggregate 40 mm nominal size)
| B/F Page- 3 /TCMB | cum | 0.32
| C/O Page- 24 /TCMB | cum | 0.32
10 | Providing and laying in position machine batched and machine mixed design mix M-25 grade cement concrete for reinforced cement concrete work, using cement content as per approved design mix, including pumping of concrete to site of laying but excluding the cost of centering, shuttering, finishing and reinforcement, including admixtures in recommended proportions as per IS: 9103 to accelerate, retard setting of concrete, improve workability without impairing strength and durability as per direction of Engineer-in-charge (Note :- Cement content considered in this item is @ 330 kg/cum. Excess/less cement used as per design mix is payable/recoverable separately).
10.1 | All works upto plinth level.
| B/F Page- 7 /TCMB | sqm | 33.27
| C/O Page- 25 /TCMB | sqm | 33.27
11 | Centring and shuttering including strutting, propping etc. and removal of form for :
11.1 | Foundations, footings, bases of columns, etc. for mass concrete.
| B/F Page- 8 /TCMB | sqm | 22.8
| C/O Page- 26 /TCMB | sqm | 22.8
12 | Steel reinforcement for R.C.C. work including straightening, cutting, bending, placing in position and binding all complete.
12.1 | Thermo-Mechanically Treated bars.in foundation upto plinth level.
| B/F Page- 6 /TCMB | Kg | 4787.45
| C/O Page- 27 /TCMB | Kg | 4787.45
14 | Brick work with common burnt clay F.P.S. (non modular) bricks of class designation 7.5 in superstructure above plinth level up to floor V level in all shapes and sizes in :
14.1 | Cement mortar 1:6 (1 cement : 6 coarse sand)
| B/F Page- 12 /TCMB | cum | 19.97
| C/O Page- 27 /TCMB | cum | 19.97
26 | Steel work in built up tubular ( round, square or rectangular hollow tubes etc.) trusses etc. including cutting, hoisting, fixing in position and applying a priming coat of approved steel primer, including welding and bolted with special shaped washers etc. complete.
26.1 | Hot finished welded type tubes
| B/F Page- 10 /TCMB | Kg | 3643.36
| C/O Page- 29 /TCMB | Kg | 3643.36
29 | Steel work welded in built up sections/ framed work including cutting, hoisting, fixing in position and applying a priming coat of approved steel primer using structural steel etc. as required.
29.1 | In gratings, frames, guard bar, ladder, railings, brackets, gates and similar works.
| B/F Page- 11 /TCMB | Kg | 15.83
| C/O Page- 30 /TCMB | Kg | 15.83
47 | Providing and fixing soil, waste and vent pipes :
47.1 | 100 mm dia.
47.1.1 | Centrifugally cast (spun) iron socket & spigot (S&S) pipe as per IS: 3989.
| B/F Page- 13 /TCMB | mtr | 129.42
| C/O Page- 32 /TCMB | mtr | 129.42
56 | Providing lead caulked joints to sand cast iron/ centrifugally cast (spun) iron pipes and fittings of diameter:
56.1 | 100 mm
| B/F Page- 13 /TCMB | each | 72
| C/O Page- 32 /TCMB | each | 72
58 | Providing and fixing G.I. pipes complete with G.I. fittings and clamps, including cutting and making good the walls etc. Internal work - Exposed on wall
58.1 | 20 mm dia. nominal bore
| B/F Page- 15 /TCMB | mtr | 160.72
| C/O Page- 33 /TCMB | mtr | 160.72
59 | Providing and fixing G.I. pipes complete with G.I. fittings and clamps including making good the walls etc. concealed pipe including painting with anti corrosive bitumastic paint, cutting chases and making good the wall.
59.1 | 15 mm dia nominal bore
| B/F Page- 14 /TCMB | mtr | 7.48
| C/O Page- 33 /TCMB | mtr | 7.48
65 | Providing and fixing G.I. Union in existing G.I. pipe line, cutting and threading the pipe and making long screws including excavation, refilling the earth or cutting of wall and making good the same complete wherever required :
65.1 | 15 mm nominal bore.
| B/F Page- 16 /TCMB | each | 16
| C/O Page- 33 /TCMB | each | 16
125 | Providing and applying two component cementitious acrylic flexible water proofing coating with Brush bond RFX of FOSROC / PIDIFIN 2K of pidilite / Master seal 550EL of BASF includingembeding polypropylene fibre matt having weight 50gms per sqm in between first and second coating of treatment including cleaning the surface all lifts and lead etc complete. Application of two component system shall be done as per manufacture's specification, recommendation and as per direction of Engineer-In-Charge.
| B/F Page- 4 /TCMB | sqm | 48.74
| C/O Page- 34 /TCMB | sqm | 48.74
EIS-1/1 | Add for using extra cement in the items of design mix over and above the specified cement content therein.
| B/F Page- 18 /TCMB | Qtl | 21.44
| C/O Page- 35 /TCMB | Qtl | 21.44
EIS-1/5 | 12 mm cement plaster finished with a floating coat of neat cement of mix :
1:4 (1 cement: 4 Coarse sand)
| B/F Page- 5 /TCMB | sqm | 48.74
| C/O Page- 36 /TCMB | sqm | 48.74
EIS-1/7 | Providing and fixing aluminium sub frame work for windows and ventilators with extruded built up standard tubular sections of approved make conforming to IS: 733 and IS: 1285, fixed with dash fastener of required dia and size (Dash fastener to be paid for separately).
| B/F Page- 17 /TCMB | kg | 747.65
| C/O Page- 36 /TCMB | kg | 747.65

## Abstract
Abstract of Cost
9th Running Account Bill
Name of work: Construction of Studio Apartment at Cozy Cot at LBSNAA,Mussoorie. (EFC Scheme No.12 A of 12th Five Year Plan).
Name of Contractor: Anil Dutt Sharma
Agmt. No. : 36/EE/MPD/2013-14 | [5 empty] | Division : MPD Mussoorie
Date of start : 03-10-2013 | [5 empty] | Sub Div : MCSD Mussoorie
Date of Completion : Work is in Progress |  |  |  |  | Stipulated Date of Completion :
Date of Abstract : 11-03-2015
Agmt item No. | Description | Qty |  |  | Amount
|  | As Per Agmt | Executed | Unit | Provision of Full Rate | Amount | Amount of Previous Bill | Since Previous
A | B | C | D | E | F | G | H | J=G-H
1 | Earth work in excavation by mechanical means (Hydraulic excavator )/ manual means over areas (exceeding 30cm in depth. 1.5m in width as well as 10 sqm on plan) including disposal of excavated earth, lead upto 50m and lift upto 1.5m, disposed earth to be levelled and neatly dressed.
1.1 | All kinds of soil
| B/F P- 47 /CMB- 256 | 879 | 1306.95
| B/F P- 20 /TCMB- |  | 5.13
|  | Total | 1312.08 | cum | 140 | 183691.2 | 182973 | 718.2
153.65
2 | Earth work in excavation/ by mechanical means (Hydraulic Excavator)/ manual means over areas (exceeding 30 cm in depth, 1.5m in width as well as 10 sqm on plan) including disposal of excavated earth, lead upto 50 m and lift upto 1.5 m, disposed earth to be levelled and neatly dressed.
2.1 | Ordinary rock
| B/F P- 47 /CMB- 256 | 293 | 194.03 | Cum | 234.91 | 45579.59 | 45579.59 | 0
6 | Extra for every additional lift of 1.5 m or part thereof in excavation /banking excavated or stacked materials.
6.1 | All kinds of soil.
| B/F P- 47 /CMB- 256 | 225 | 528.14
|  |  | 225 | Cum | 41.1 | 9247.5 | 9247.5 | 0
|  |  | 303.14 | Cum | 41.1 | 12459.05 | 12459.05 | 0
[5 empty] | C/O | 250977.34 | 250259.14 | 718.2
[5 empty] | B/F | 250977.34 | 250259.14 | 718.2
7 | Supplying and filling in plinth with Jamuna sand under floors including, watering, ramming consolidating and dressing complete.
| B/F P- 48 /CMB- 256 | 30 | 28.81 | cum | 890.09 | 25643.49 | 25643.49 | 0
8 | Providing and laying in position cement concrete of specified grade excluding the cost of centring and shuttering - All work upto plinth level :
8.1 | 1:2:4 (1 cement : 2 coarse sand : 4 graded stone aggregate 20 mm nominal size)
| B/F P- 48 /CMB- 256 | 7 | 8.81 | cum | 5362.24 | 47241.33 | 47241.33 | 0
8.2 | 1:5:10 (1 cement : 5 coarse sand : 10 graded stone aggregate 40 mm nominal size)
| B/F P- 48 /CMB- 256 | 115 | 78.81
| B/F P- 20 /TCMB- |  | 0.32
|  | Total | 79.13 | cum | 3988.26 | 315591.01 | 314314.77 | 1276.24
[5 empty] | C/O | 639453.17 | 637458.73 | 1994.44
[5 empty] | B/F | 639453.17 | 637458.73 | 1994.44
10 | Providing and laying in position machine batched and machine mixed design mix M-25 grade cement concrete for reinforced cement concrete work, using cement content as per approved design mix, including pumping of concrete to site of laying but excluding the cost of centering, shuttering, finishing and reinforcement, including admixtures in recommended proportions as per IS: 9103 to accelerate, retard setting of concrete, improve workability without impairing strength and durability as per direction of Engineer-in-charge (Note :- Cement content considered in this item is @ 330 kg/cum. Excess/less cement used as per design mix is payable/recoverable separately).
10.1 | All works upto plinth level.
| B/F P- 49 /CMB- 256 | 460 | 315.79
| B/F P- 20 /TCMB- |  | 33.27
|  | Total | 349.06 | cum | 6227.15 | 2173648.98 | 1966471.7 | 207177.28
10.2 | All works above plinth level upto floor V level
| B/F P- 49 /CMB- 256 | 621 | 366.3
|  | Total | 366.3 | cum | 6500 | 2380950 | 2380950 | 0
6867.84
[5 empty] | C/O | 5194052.15 | 4984880.43 | 209171.72
[5 empty] | B/F | 5194052.15 | 4984880.43 | 209171.72
11 | Centring and shuttering including strutting, propping etc. and removal of form for :
11.1 | Foundations, footings, bases of columns, etc. for mass concrete.
| B/F P- 50 /CMB- 256 | 329 | 244.04
| B/F P- 20 /TCMB- |  | 22.8
|  | Total | 266.84 | sqm | 198.26 | 52903.7 | 48383.37 | 4520.33
11.2 | Walls (any thickness) including attached pilasters, buttresses, plinth and string courses etc.
| B/F P- 50 /CMB- 256 | 940 | 238.98 | sqm
|  | Total | 238.98 | sqm | 338.73 | 80949.7 | 80949.7 | 0
11.3 | Suspended floors, roofs, landings, balconies and access platform.
| B/F P- 50 /CMB- 256 | 1424 | 886.04 | sqm | 369.67 | 327542.41 | 327542.41 | 0
11.5 | Lintels, beams, plinth beams, girders, bressumers and cantilevers.
| B/F P- 50 /CMB- 256 | 1577 | 1505.53
|  | Total | 1505.53 | sqm | 311.53 | 469017.76 | 469017.76 | 0
11.6 | Columns, Pillars, Piers, Abutments, Posts and Struts.
| B/F P- 50 /CMB- 256 | 934 | 839.34 | sqm | 434.3 | 364525.36 | 364525.36 | 0
11.7 | stairs, (excluding landing) except spiral-staircases
| B/F P- 50 /CMB- 256 | 73 | 57.53
|  | Total | 57.53 | sqm | 387.61 | 22299.2 | 22299.2 | 0
[5 empty] | C/O | 6511290.28 | 6297598.23 | 213692.05
[5 empty] | B/F | 6511290.28 | 6297598.23 | 213692.05
11.8 | Edges of slabs and breaks in floors and walls.
11.8.1 | Under 20 cm wide
| B/F P- 51 /CMB- 256 | 19 | 52.52
|  | Total | 52.52 | Metre | 90 | 4726.8 | 4726.8 | 0
118.14
12 | Steel reinforcement for R.C.C. work including straightening, cutting, bending, placing in position and binding all complete.
12.1 | Thermo-Mechanically Treated bars.in foundation upto plinth level.
B: B/F P- 51 /CMB- 256; C: 80500; D: 41003.71 | 6903.35
| B/F P- 20 /TCMB- |  | 4787.45
|  | Total | 45791.16 | kg | 73.95 | 3386256.28 | 3032224.35 | 354031.93
#REF!
12.2 | Thermo-Mechanically Treated bars. above plinth level.
| B/F P- 51 /CMB- 256 | 108675 | 57604.11
|  | Total | 57604.11 | kg | 73.95 | 4259823.93 | 4259823.93 | 0
13 | Brick work with common burnt clay F.P.S. (non modular) bricks of class designation 7.5 in foundation and plinth in:
13.2 | Cement mortar 1:6 (1 cement : 6 coarse sand)
| B/F P- 51 /CMB- 256 | 21 | 6.68 | cum | 3939.73 | 26317.4 | 26317.4 | 0
14 | Brick work with common burnt clay F.P.S. (non modular) bricks of class designation 7.5 in superstructure above plinth level up to floor V level in all shapes and sizes in :
14.1 | Cement mortar 1:6 (1 cement : 6 coarse sand)
| B/F P- 51 /CMB- 256 | 271 | 284.69
| B/F P- 21 /TCMB- |  | 19.97
|  | Total | 304.66 | cum | 4300 | 1310038 | 1224167 | 85871
4604.48
[5 empty] | C/O | 15498452.69 | 14844857.71 | 653594.98
[5 empty] | B/F | 15498452.69 | 14844857.71 | 653594.98
15 | Half brick masonry with common burnt clay F.P.S. (non modular) bricks of class designation 7.5 in superstructure above plinth level up to floor V level.
15.1 | cement mortar 1:4 (1 cement : 4 coarse sand)
| B/F P- 52 /CMB- 256 | 987 | 491.76
|  | Total | 491.76 | Sqm | 525 | 258174 | 258174 | 0
566.45
16 | Random rubble masonry with hard stone in foundation and plinth including levelling up with cement concrete 1:6:12 (1 cement : 6 coarse sand : 12 graded stone aggregate 20mm nominal size) at plinth level with :
16.1 | Cement mortar 1:6 (1 cement : 6 coarse sand)
| B/F P- 52 /CMB- 256 | 78 | 205.87 | cum | 3400 | 699958 | 699958 | 0
3634.02
17 | Placing and packing of available rock/ stone pieces behind the retaining walls at any height and depth as per direction of Engineer-in-Charge.
| B/F P- 52 /CMB- 256 | 285 | 26.57 | cum | 396.05 | 10523.05 | 10523.05 | 0
[5 empty] | C/O | 16467107.74 | 15813512.76 | 653594.98
[5 empty] | B/F | 16467107.74 | 15813512.76 | 653594.98
19 | Providing wood work in frames of doors, windows, clerestory windows and other frames, wrought framed and fixed in position with hold fast lugs or with dash fasteners of required dia & length ( hold fast lugs or dash fastener shall be paid for separately).
19.1 | Second class teak wood
| B/F P- 53 /CMB- 256 | 7.3 | 3.52
|  | Total | 3.52 | cum | 100000 | 352000 | 352000 | 0
101937.62
26 | Steel work in built up tubular ( round, square or rectangular hollow tubes etc.) trusses etc. including cutting, hoisting, fixing in position and applying a priming coat of approved steel primer, including welding and bolted with special shaped washers etc. complete.
26.1 | Hot finished welded type tubes
| B/F P- 53 /CMB- 256 | 14346 | 10102.05
| B/F P- 21 /TCMB- |  | 3643.36
|  | Total | 13745.41 | Kg | 99 | 1360795.59 | 1000102.95 | 360692.64
101.09
28 | Providing and fixing circular/ Hexagonal cast iron or M.S. sheet box for ceiling fan clamp of internal dia 140mm, 73mm height, top lid of 1.5mm thick M.S. sheet with its top surface hacked for proper bonding, top lid shall be screwed into the cast iron/ M.S. sheet box by means of 3.3mm dia. round headed screws, one lock at the corners. Clamp shall be made of 12mm dia M.S. bar bent to shape as per standard drawing.
| B/F P- 53 /CMB- 256 | 42 | 42 | each | 139.52 | 5859.84 | 5859.84 | 0
[5 empty] | C/O | 18185763.17 | 17171475.55 | 1014287.62
[5 empty] | B/F | 18185763.17 | 17171475.55 | 1014287.62
29 | Steel work welded in built up sections/ framed work including cutting, hoisting, fixing in position and applying a priming coat of approved steel primer using structural steel etc. as required.
29.1 | In gratings, frames, guard bar, ladder, railings, brackets, gates and similar works.
| B/F P- 54 /CMB- 256 | 6220 | 5857.06
| B/F P- 21 /TCMB- |  | 15.83
|  | Total | 5872.89 | Kg | 90 | 528560.1 | 527135.4 | 1424.7
92.54
35 | Providing and fixing precoated galvanised iron profile sheets (size, shape and pitch of corrugation as approved by Engineer-in-charge) 0.50 mm + 0.05 %, total coated thickness with zinc coating 120 gsm as per IS: 277 in 240 mpa steel grade, 5-7 microns epoxy primer on both side of the sheet and polyester top coat 15-18 microns. Sheet should have protective guard film of 25 microns minimum to avoid scratches while transportation and should be supplied in single length upto 12 metre or as desired by Engineer-in-charge. The sheet shall be fixed using self drilling /self tapping screws of size (5.5x 55mm) with EPDM seal, complete upto any pitch in horizontal/ vertical or curved surfaces excluding the cost of purlins, rafters and trusses and including cutting to size and shape wherever required.
| B/F P- 54 /CMB- 256 | 479 | 416.57 | sqm | 690 | 287433.3 | 287433.3 | 0
714.82
[5 empty] | C/O | 19001756.57 | 17986044.25 | 1015712.32
[5 empty] | B/F | 19001756.57 | 17986044.25 | 1015712.32
36 | Providing and fixing precoated galvanised steel sheet roofing accessories 0.50 mm + 0.05 % total coated thickness, Zinc coating 120gsm as per IS: 277 in 240 mpa steel grade, 5-7 microns epoxy primer on both side of the sheet and polyester top coat 15-18 microns using self drilling/ self tapping screws complete :
36.1 | Ridges plain (500 - 600mm).
| B/F P- 55 /CMB- 256 | 33 | 47.1 | mtr | 700 | 32970 | 32970 | 0
737.39
36.3 | Gutter .(600 mm over all girth).
| B/F P- 55 /CMB- 256 | 66 | 76.4 | mtr | 860 | 65704 | 65704 | 0
891.76
45 | Providing and applying 12 mm thick (average) premixed formulated one coat gypsum lightweight plaster having additives and light weight aggregates as vermiculite/ perlite respectively conforming to IS: 2547 (Part - 1 & II) 1976 (made by standard companies such as Gyproc of Saint Gobain, Ferrous crete India Pvt. Ltd. or Shri Ram cement or equivalent as per approval of Engineer-in-charge), applied on hacked / uneven background such as bare brick/ block/ RCC work on walls & ceiling at all floors and locations, finished in smooth line and level etc. complete.
(a) | 6 mm
| B/F P- 55 /CMB- 256 | 1615 | 410.7 | sqm | 165 | 67765.5 | 67765.5 | 0
172.84
(b) | 12 mm
| B/F P- 55 /CMB- 256 | 1232 | 289.71 | sqm | 250 | 72427.5 | 72427.5 | 0
254.69
(c ) | 15 mm
| B/F P- 55 /CMB- 256 | 2063 | 366.49 | sqm | 290 | 106282.1 | 106282.1 | 0
295.67
[5 empty] | C/O | 19346905.67 | 18331193.35 | 1015712.32
[5 empty] | B/F | 19346905.67 | 18331193.35 | 1015712.32
47 | Providing and fixing soil, waste and vent pipes :
47.1 | 100 mm dia.
47.1.1 | Centrifugally cast (spun) iron socket & spigot (S&S) pipe as per IS: 3989.
| B/F P- 56 /CMB- 256 | 364 | 58.8
| B/F P- 21 /TCMB- |  | 129.42
|  | Total | 188.22 | mtr | 900 | 169398 | 52920 | 116478
1018.39
50 | Providing and fixing plain bend of required degree.
50.1 | 100 mm
50.1.1 | Sand cast iron S&S as per IS : 3989
| B/F P- 56 /CMB- 256 | 42 | 15 | each | 350 | 5250 | 5250 | 0
352.03
52 | Providing and fixing single equal plain junction of required degree with access door, insertion rubber washer 3 mm thick, bolts and nuts complete.
52.1 | 100x100x100 mm
52.1.1 | Sand cast iron S&S as per IS - 3989
| B/F P- 56 /CMB- 256 | 55 | 32 | each | 680 | 21760 | 21760 | 0
688.69
53 | Providing and fixing single equal plain junction of required degree :
53.1 | 100x100x100 mm
53.1.1 | Sand cast iron S&S as per IS - 3989
| B/F P- 56 /CMB- 256 | 24 | 15 | each | 600 | 9000 | 9000 | 0
621.09
56 | Providing lead caulked joints to sand cast iron/ centrifugally cast (spun) iron pipes and fittings of diameter:
56.1 | 100 mm
| B/F P- 56 /CMB- 256 | 406 | 150
| B/F P- 21 /TCMB- |  | 72
|  | Total | 222 | each | 230 | 51060 | 34500 | 16560
246.91
[5 empty] | C/O | 19603373.67 | 18454623.35 | 1148750.32
[5 empty] | B/F | 19603373.67 | 18454623.35 | 1148750.32
57 | Providing and fixing trap of self cleansing design with screwed down or hinged grating with or without vent arm complete, including cost of cutting and making good the walls and floors :
57.1 | 100 mm inlet and 100 mm outlet
57.1.1 | Sand cast iron S&S as per IS: 3989.
| B/F P- 57 /CMB- 256 | 72 | 45 | each | 930 | 41850 | 41850 | 0
952.34
58 | Providing and fixing G.I. pipes complete with G.I. fittings and clamps, including cutting and making good the walls etc. Internal work - Exposed on wall
58.1 | 20 mm dia. nominal bore
| B/F P- 21 /TCMB- | 384 | 160.72 | mtr | 200 | 32144 | 0 | 32144
223.38
59 | Providing and fixing G.I. pipes complete with G.I. fittings and clamps including making good the walls etc. concealed pipe including painting with anti corrosive bitumastic paint, cutting chases and making good the wall.
59.1 | 15 mm dia nominal bore
| B/F P- 57 /CMB- 256 | 600 | 311.7
| B/F P- 21 /TCMB- |  | 7.48
|  | Total | 319.18 | mtr | 250 | 79795 | 77925 | 1870
273.22
65 | Providing and fixing G.I. Union in existing G.I. pipe line, cutting and threading the pipe and making long screws including excavation, refilling the earth or cutting of wall and making good the same complete wherever required :
65.1 | 15 mm nominal bore.
| B/F P- 57 /CMB- 256 | 24 | 32
| B/F P- 21 /TCMB- |  | 16
|  | Total | 48 | each | 120 | 5760 | 4546.24 | 1213.76
142.07
103 | Providing and fixing CP Brass high flow single lever consealed divertor for bath and shower system Jaquar make (VGN-CHR-27079 & ALD-CHR-79 ) or equivalent of approved quality complete as per direction of Engineer-In-Charge.
| B/F P- 57 /CMB- 256 | 24 | 15 | each | 4500 | 67500 | 67500 | 0
4882.3
[5 empty] | C/O | 19830422.67 | 18646444.59 | 1183978.08
[5 empty] | B/F | 19830422.67 | 18646444.59 | 1183978.08
125 | Providing and applying two component cementitious acrylic flexible water proofing coating with Brush bond RFX of FOSROC / PIDIFIN 2K of pidilite / Master seal 550EL of BASF includingembeding polypropylene fibre matt having weight 50gms per sqm in between first and second coating of treatment including cleaning the surface all lifts and lead etc complete. Application of two component system shall be done as per manufacture's specification, recommendation and as per direction of Engineer-In-Charge.
| B/F P- 58 /CMB- 256 | 211 | 117.26
| B/F P- 22 /TCMB- |  | 48.74
|  | Total | 166 | sqm | 315 | 52290 | 36936.9 | 15353.1
354.1
132 | Demolishing the existing old structure at site for the "Construction of studio apartments for Cozy cotat LBSNAA, Mussoorie." as mentioned below, including removing the serviceable and unserviceable materials. The dismantling has to be carried out right upto the foundation and trenches will have to be filled up by earth including consolidation of the earth and making the surface of earth good to the satisfaction of the eingineer in charge. The following buildings to be demolished:-
132.1 | Old Cozy cot (D/S) Building at LBSNAA Mussoorie.
| B/F P- 58 /CMB- 256 | 1 | 1 | Job | -297041 | -297041 | -297041 | 0
Total Amount | [5 empty] | 19585671.67 | 18386340.49 | 1199331.18
| Add % of clause 12 i.e 6.07% above For civil work |  |  | 18386340.49 |  | 1188850.27 | 1116050.87 | 72799.4
| Total Amount |  |  |  |  | 20774521.94 | 19502391.36 | 1272130.58
[5 empty] | B/F | 20774521.94 | 19502391.36 | 1272130.58
Extra Items
EIS NO 1 sanctioned vide No
EIS-1/1 | Add for using extra cement in the items of design mix over and above the specified cement content therein.
| B/F P- 59 /CMB- 256 |  | 321.93
| B/F P- 22 /TCMB- |  | 21.44
| EIS No. -I appvd by EE | Total | 343.37 | Qtl | 652.76 | 224138.2 | 210143.03 | 13995.17
EIS-1/2 | Centring and shuttering including strutting, propping etc. and removal of form for :
Weather shade, Chajjas, corbels etc., including edges
| B/F P- 59 /CMB- 256 |  | 74.43
|  |  | 74.43 | sqm | 400 | 29772 | 29772 | 0
EIS-1/3 | Providing and fixing mild steel round holding down bolts with nuts and washer plates complete.
| B/F P- 59 /CMB- 256 |  | 177.86 | kg | 60 | 10671.6 | 10671.6 | 0
EIS-1/4 | Providing 40x5 mm flat iron hold fast 40 cm long including fixing to frame with 10 mm diameter bolts, nuts and wooden plugs and embeddings in cement concrete block 30x10x15cm 1:3:6 mix (1 cement : 3 coarse sand : 6 graded stone aggregate 20mm nominal size)
| B/F P- 59 /CMB- 256 |  | 576
|  | Total | 576 | each | 100 | 57600 | 57600 | 0
[5 empty] | C/O | 21096703.74 | 19810577.99 | 1286125.75
[5 empty] | B/F | 21096703.74 | 19810577.99 | 1286125.75
EIS-1/5 | 12 mm cement plaster finished with a floating coat of neat cement of mix :
1:4 (1 cement: 4 Coarse sand)
| B/F P- 60 /CMB- 256 |  | 117.26
| B/F P- 22 /TCMB- |  | 48.74
|  | Total | 166 | sqm | 150 | 24900 | 17589 | 7311
EIS-1/6 | Providing and fixing bolts including nuts and washers complete.
| B/F P- 60 /CMB- 256 |  | 240.24 | kg | 86 | 20660.64 | 20660.64 | 0
EIS-1/7 | Providing and fixing aluminium sub frame work for windows and ventilators with extruded built up standard tubular sections of approved make conforming to IS: 733 and IS: 1285, fixed with dash fastener of required dia and size (Dash fastener to be paid for separately).
| B/F P- 22 /TCMB- |  | 747.65 | kg | 250 | 186912.5 | 0 | 186912.5
[6 empty] | 21329176.88 | 19848827.63 | 1480349.25
[5 empty] | Say | 21329177 | 19848828 | 1480349
| Add amount deposited in D.O against Item No.132 Vide DD No.000938 dated 6.11.13 of Bank of IDBI |  |  |  |  | 315071 | 315071 | 0
[6 empty] | 21644248 | 20163899 | 1480349
| Less Amount of 8th RA Bill Vide CV No. 39 Dated:17-03-2015 |  |  |  |  | -20163899
| Work Done in this bill |  |  |  |  | 1480349
Secured Advance
1 | TMT Bars
i) | Qty. outstanding from previous bill |  | 27960 | Kg
ii) | Less Qty. utilised in work from previous bill |  | -5000 | Kg
iii) | Add Qty. brought at site since previous bill |  | 0 | Kg
iv) | Qty. outstanding in this bill |  | 22960 | Kg
|  | @ | 42.07 | P.R |  | 965927
|  |  | 47.16 | F.R
2 | GRANITE STONE SLAB 18 mm Thick ( LAKHA RED )
i) | Qty. outstanding from previous bill |  | 420.54 | sqm
ii) | Less Qty. utilised in work from previous bill |  | 0
iii) | Add Qty. brought at site since previous bill |  | 0
iv) | Qty. outstanding in this bill |  | 420.54
|  | @ | 2324.16 | P.R |  | 977402
|  |  | 2582.4 | F.R
3 | Vritified tile 600 x 600
i) | Qty. outstanding from previous bill |  | 0 | sqm
ii) | Less Qty. utilised in work from previous bill |  | 0
iii) | Add Qty. brought at site since previous bill |  | 972
iv) | Qty. outstanding in this bill |  | 972
|  | @ | 871.2 | P.R |  | 846806
|  |  | 968 | F.R
4 | Wall tile 300x 600
i) | Qty. outstanding from previous bill |  | 0 | sqm
ii) | Less Qty. utilised in work from previous bill |  | 0
iii) | Add Qty. brought at site since previous bill |  | 522
iv) | Qty. outstanding in this bill |  | 522
|  | @ | 670.83 | P.R |  | 350173
|  |  | 745.37 | F.R
3140308
| Less Amount Outstanding in Previous bill |  |  |  |  | -2153679
| Amount of Secured Advance in this Bill |  |  |  |  | 986629

## recovery (2)
Recovery Statement
|  |  |  | Gross work done |  | 21644248
| Less Amount of 8th RA Bill Vide CV No. 39 Dated:17-03-2015 |  |  |  |  | -20163899
| Work Done in thid Bill |  |  |  |  | 1480349
| Amount of secured Advacce |  |  |  |  | 986629
2466978
1 | Security Deposit @ 5.00% on |  | 1082212
21644248
| Less EMD Already Deposited |  | -1018655
| Now to be recovered |  | 63557 | 63557
2 | Income Tax @ 2% on G.V. |  | 432885
| Already recovered |  | -403278
| Now to be recovered |  | 29607 | 29607
3 | Education Cess @ 2% on S.P. |  | 592 | 592
| Cess for intermediate and higher edu. @ 1% |  | 296 | 296
4 | Sales Tax @ 2% on G.V. |  | 432885
| Already recovered |  | -403278
| Now to be recovered |  | 29607 | 29607
5 | Contractor labour welfare fund 1% on Since Preivous |  | 14803 | 14803
6 | Withheld for Mile stone @ 3% on T.A(Civil) (For Three mile stone) |  | 1629312
| Less already recovered in 5th R.A.bill CMB No.221 P-62 |  | -1629312
| Now to be recovered in this bill |  | 0 | 0
7 | Withheld for SE's inspection/Q.C. para |  | 200000
| Less Already recovered | ` | -200000
| Now to be recovered in this bill |  | 0 | 0
| Total Recoveries |  |  | 138462
| Net Payable |  | 2466978 | -138462 | ` | 2328516
CERTIFIED THAT :-
1) | The work has been carried out as per terms & condtions of the Agreement.
2) | No T&P has been issued to the contractor.
3) | No labour complaint has been recieved against the contactor so far.
4) | Clause 36 complied by the contractor.
5) | Water arranged by the contractor.
6) | All Mandatory tests has been carried out and report awaited.

## TESTCHECK
TEST CHECK STATEMENT
9th RA Bill
| DIVISION: MPD, CPWD |  |  |  |  | SUB-DIV | MPSD
Name of work: Construction of Studio Apartment at Cozy Cot at LBSNAA,Mussoorie. (EFC Scheme No.12 A of 12th Five Year Plan).
#REF!
#REF!
SN | Description of Items | Ref. of MB & Pages | Qty. | Amount of AE Test Check | Amount of EE test check | Remarks
1 | Upto 8th RA |  |  | 17159615 | 4352191
2 | 9th RA | P-4/CMB-267 |  | 18306
|  | P-6/CMB-267 |  | 375522
|  | P-7/CMB-267 |  | 219753
|  | P-9-10/CMB-267 |  | 614959
|  | Total |  | 18388155 | 4352191
| GROSS VALUE OF WORK DONE |  |  | 21644248
TEST CHECK BY AE MORE THAN 50%
lgk;d vfHk;ark]
elwjh ifj;kstuk mieaMy]
dsyksfufo] yk-c-'kk-jk-iz-vdkneh]
elwjhA

## cement (2)
STATEMENT OF THEORETICAL CALCULATIONS OF CEMENT CONSUMPTION
Name of work: Construction of Studio Apartment at Cozy Cot at LBSNAA,Mussoorie. (EFC Scheme No.12 A of 12th Five Year Plan).
Name of Contractor: Anil Dutt Sharma |  |  |  | Division : MPD Mussoorie
Agmt. No. : 36/EE/MPD/2013-14 |  |  |  | Sub Div : MPSD Mussoorie
Sl no. of this bill : 8th R.A. bill
Item no. | BRIEF DESCRIPTION | QTY. |  | COFFICIENT | Unit |  | CEMENT REQUIRED
8.1 | P/L C.C.1:2:4 in foundation | 8.81 | Cum | 3.2 | 1 | Cum | 28.19
8.2 | P/L C.C.1:5:10 in foundation | 79.13 | Cum | 1.3 | 1 | Cum | 102.87
10.1 | P/L Design mix M25 | 349.06 | Cum | 3.3 | 1 | Cum | 1151.9
10.2 | P/L Design mix M25 | 366.3 | Cum | 3.3 | 1 | Cum | 1208.79
13.1 | Brick work 1:6 | 6.68 | Cum | 0.625 | 1 | Cum | 4.18
14.1 | B/W in super structure in CM 1:6 | 304.66 | cum | 0.625 | 1 | Cum | 190.41
15.1 | Half brick in super structure in CM 1:4 | 491.76 | Sqm | 10.64 | 100 | Sqm | 52.32
16.1 | RR Masonry......CM 1:6 | 205.87 | Cum | 0.825 | 1 | Cum | 169.84
| Extra cement 3.80-3.30=0.50 | 715.36 | cum | 0.5 | 1 | Cum | 357.68
| CC 1:3:6 for Bond stone | 13.85 | Cum | 2.2 | 1 | Cum | 30.47 | 142500
EIS 1/4 | P/F Hold Fast | 576 | each | 1.1 | 100 | each | 6.34
EIS 1/5 | 12mm Plaster 1:4 | 166 | Sqm | 7.67 | 100 | sqm | 12.73
[7 empty] | 3315.72 | 28750
|  |  |  | Says |  |  | 6631 | 171250
Bags
Cement consumed as per cement resister 6700 Bags some work yet to be measured.

## steel
Annexure -III
STEEL CONSUMPTION STATEMENT
Name of work: Construction of Studio Apartment at Cozy Cot at LBSNAA,Mussoorie. (EFC Scheme No.12 A of 12th Five Year Plan).
Name of Contractor: Anil Dutt Sharma | [5 empty] | Division : MPD Mussoorie
Agmt. No. : 36/EE/MPD/2013-14 | [5 empty] | Sub Div : MPSD Mussoorie
Sl no. of this bill : 9th R.A. bill
S.N. | Reference | 8Ø | 10Ø | 12Ø | 16Ø | 20Ø | 25Ø | TOTAL
1 | upto previous bill | 13610.63 | 23311.22 | 12610.71 | 11969.7 | 26138.69 | 10965.9 | 98606.85
2 | in this bill item 12.2.P- 6 TCMB-267 | 858.65 | 196.45 | 34.63 | 2108.13 | 0 | 1589.59 | 4787.45
0
| Total | 14469.28 | 23507.67 | 12645.34 | 14077.83 | 26138.69 | 12555.49 | 103394.3
| Add 3% for wastage | 434.08 | 705.23 | 379.36 | 422.33 | 784.16 | 376.66 | 3101.83
|  | 14903.36 | 24212.9 | 13024.7 | 14500.16 | 26922.85 | 12932.15 | 106496.13
| Add 2% for variations | 298.07 | 484.26 | 260.49 | 290 | 538.46 | 258.64 | 2129.92
| Total | 15201.43 | 24697.16 | 13285.19 | 14790.16 | 27461.31 | 13190.79 | 108626.05
| Qty. Consumed in work i/c wastages and variations | 15.201 | 24.697 | 13.285 | 14.79 | 27.461 | 13.19 | 108.626
|  |  | MT | MT | MT | MT | MT | MT
B | Qty. received upto date | 20.94 | 25.28 | 18.66 | 26.06 | 28.28 | 19.54 | 131.48
|  |  |  | MT |  |  |  | MT

## Mand (2)
STATEMENT OF MANDATORY TESTS
Name of work: Construction of Studio Apartment at Cozy Cot at LBSNAA,Mussoorie. (EFC Scheme No.12 A of 12th Five Year Plan).
Name of Contractor: Anil Dutt Sharma |  |  | Division : MPD Mussoorie
Agmt. No. : 36/EE/MPD/2013-14 |  |  | Sub Div : MPSD Mussoorie
Sl no. of this bill : 9th R.A. bill
Sl No. | Item | Frequency as per specification | Upto date work done qty | No. of test required | No. of tests actually done | Remarks
1 | Test for Cube strength of C.C | 10 | 715 | 72 | 95
2 | Slump Test | each/day | 715 | 48 | 48
3 | Test for Particle Size Distribution of stone aggregate 40mm N.S | 45 | 75 | 2 | 3
4 | Test for Particle Size Distribution of stone aggregate 20mm N.S | 50 | 700 | 14 | 16
5 | Test for Particle Size Distribution of Coarse Sand | 40 | 500 | 13 | 14
6 | Test for silt content Coarse sand | 20 | 500 | 25 | 31
7 | Test for Deleterious Material | 45 | 770 | 18 | 24
8 | Test for Water | 3 Months | 0 | 4 | 4
9 | Test for Cement | 50 | 372 | 8 | 9
10 | Test for reiforcement | 25 | 131.48 | 6 | 6
11 | Bricks | 50000 Nos. | 172000 | 4 | 4

## SIS-I (2)
SUBSTITUTE ITEM STATEMENT No-I
Name of work: Construction of Studio Apartment at Cozy Cot at LBSNAA,Mussoorie. (EFC Scheme No.12 A of 12th Five Year Plan).
Agmt. No. : 36/EE/MPD/2013-14
Name of Contractor: Anil Dutt Sharma
Estimated Cost:- 49016914 + 1915845/-
Tendered Cost :- 519241 + 2318172/- | [7 empty] | Amount of this statement |  |  |  | ` | 1196701
Percentage under Clause 12 : 6.07% above (Civil Work DSR 2012 + 18.79%) | [8 empty] | Total |  |  | ` | 1196701
| As per Agreement | [6 empty] | As per Substituted |  |  |  |  | Remarks
Sl.No | Agmt No. | Description of Item | Qty. | Unit | Rate | Amount |  | Description of Item | Qty. | Unit | Rate | Amount
1 | 45 | Providing and applying 12 mm thick (average) premixed formulated one coat gypsum lightweight plaster having additives and light weight aggregates as vermiculite/ perlite respectively conforming to IS: 2547 (Part - 1 & II) 1976 (made by standard companies such as Gyproc of Saint Gobain, Ferrous crete India Pvt. Ltd. or Shri Ram cement or equivalent as per approval of Engineer-in-charge), applied on hacked / uneven background such as bare brick/ block/ RCC work on walls & ceiling at all floors and locations, finished in smooth line and level etc. complete. |  |  |  |  | Agmt. 40.1 | [5 empty] | Item Subsititure as per direction of CE NZ-IV during inspection on 28-02-2015.
| (a) | 6 mm | 1204.3 | sqm | 183.33 | 220784 |  | 6 mm Cement Plaster 1:3 (1 Cement : 3 Fine Sand) | 880.1 | Sqm | 127.26 | 112002 | Rate as per agmt. No. 40.1 upto permissable limited.
[9 empty] | 1565.59 | sqm | 137.39 | 215096 | Rate as per susitution clause 12.
[9 empty] | Balance Qty | sqm | 126.9 |  | As per market rate.
| (b) | 12 mm | 942.29 | sqm | 270.15 | 254560 | Agmt. 38.1 | 12 mm Cement Plaster 1:6 (1 Cement : 6 Fine Sand) | 1729.7 | sqm | 141.75 | 245185 | Rate as per agmt. No. 38.1 upto permissable limited.
[9 empty] | 1224.98 | sqm | 164.87 | 201962 | Rate as per susitution clause 12.
[9 empty] | Balance Qty | sqm | 149.41 |  | As per market rate.
| (c ) | 15 mm | 1696.51 | sqm | 313.62 | 532059 | 3 | 15 mm cement plaster on the rough side of single or half brick wall with cement mortar 1:6 (1 Cement : 6 Fine Sand) | 2205.46 | sqm | 191.55 | 422456 | As per subsitution clasue12
[9 empty] | Balance Qty | sqm | 173.6 |  | As per market rate.
|  | Total |  |  |  | 1007403 |  | Total |  |  |  | 1196701
Certified that :-
1- | This statement contain item 03 items only.
2- | The rates are net and not subjected to any abatement/anhancement.
3- | The payment shall be made as per the sanctioned rate for sanctioned quantity executed at site of work within the permissible limits of variation.
4- | The rates adopted are lowest prevailing market rates
|  | Subsititute Item Statement No. I is |  |  |  |  | 1196701

## part rate
Annexure -I/1
PART RATE STATEMENT
Name of work: Construction of Studio Apartment at Cozy Cot at LBSNAA,Mussoorie. (EFC Scheme No.12 A of 12th Five Year Plan).
Name of Contractor: Anil Dutt Sharma |  |  | Division : MPD Mussoorie
Agmt. No. : 36/EE/MPD/2013-14 |  |  | Sub Div : MPSD Mussoorie
Sl no. of this bill : 8th R.A. bill
Item no. | BRIEF DESCRIPTION | Full rate | Part rate in previous bill | Part rate in this bill | Reason
1.1 | Eath work over areas -all kind of soil | 153.65 | 140 | 140 | deposited earth to be levelled
10.2 | RCC All works above plinth level upto floor V level | 6867.84 | 6500 | 6500 | Repair of edges yet to be done
11.8 | Edges of slabs and breaks in floors and walls under 20 cm | 118.14 | 90 | 90 | Deviation yet to be approved
14.1 | B/W in super structure in CM 1:6 | 4604.48 | 4300 | 4300 | curing in progress
15.1 | H/B mansonry in super structure in CM 1:4 | 566.45 | 525 | 525 | curing in progress
16.1 | RR Masonry ...CC in 1:6 | 3634.02 | 3400 | 3400 | Deviation yet to be approved
19.1 | Second class teak wood | 101937.62 | 100000 | 100000 | Adjustment of line and level
26.1 | Steel work in built up tubular ( round, square or rectangular hollow tubes etc.) trusses etc. including cutting, hoisting, fixing in position and applying a priming coat of approved steel primer, including welding and bolted with special shaped washers etc. complete. | 101.09 | 99 | 99 | grinding of joint at some places
29.1 | Steel work welded in built up sections/ framed work including cutting, hoisting, fixing in position and applying a priming coat of approved steel primer using structural steel etc. as required. | 92.54 | 90 | 90 | grinding of joint at some places
35 | precoated galvanised iron profile sheets | 714.82 | 690 | 690 | more Screws required
36.1 | Ridges plain (500 - 600mm). | 737.39 | 700 | 700 | more Screws required
36.3 | Gutter .(600 mm over all girth). | 891.76 | 860 | 860 | Filling of joints
45 | Plaster 6 mm | 172.84 | 165 | 165 | edge repair
(b) | Plaster 12 mm | 254.69 | 250 | 250 | edge repair
(c ) | Plaster 15 mm | 295.67 | 290 | 290 | edge repair
47.1.1 | Providing and fixing soil, waste and vent pipes : 100 mm dia. | 1018.39 | 900 | 900 | Testing yet to be done
50.1.1 | Providing and fixing plain bend of required degree. 100 mm | 352.03 | 350 | 350 | Testing yet to be done
52.1.1 | Providing and fixing single equal plain junction of required degree with access door, 100x100x100 mm | 688.69 | 680 | 680 | Testing yet to be done
53.1.1 | Providing and fixing single equal plain junction of required degree : 100x100x100 mm | 621.09 | 600 | 600 | Testing yet to be done
56.1 | Providing lead caulked joints to sand cast iron/ centrifugally cast (spun) iron pipes and fittings of diameter: 100 mm | 246.91 | 230 | 230 | Testing yet to be done
58.1 | Providing and fixing G.I. pipes complete with G.I. fittings and clamps, including cutting and making good the walls etc. Internal work - Exposed on wall | 223.38 | 200 | 200
57.1.1 | Providing and fixing trap of self cleansing design 100 mm inlet and 100 mm outlet | 952.34 | 930 | 930 | Testing yet to be done
59.1 | G.I. Pipe 15 mm nominal bore | 273.22 | 250 | 250 | Testing yet to be done
65.1 | Providing and fixing G.I. Union in existing G.I. pipe line, cutting and threading the pipe and making long screws including excavation, refilling the earth or cutting of wall and making good the same complete wherever required : | 142.07 | 120 | 120
103 | Providing and fixing CP Brass high flow single lever consealed divertor for bath and shower system Jaquar make (VGN-CHR-27079 & ALD-CHR-79 ) | 4882.3 | 4500 | 4500 | Testing yet to be done
125 | Providing and applying two component cementitious acrylic flexible water proofing coating with Brush bond RFX of FOSROC / PIDIFIN 2K of pidilite / Master seal 550EL of BASF | 354.1 | 315 | 315 | Testing yet to be done
EIS 1/3 | P/F mild steel round holding down bolt |  | 60 | 60 | Item not sanctioned
EIS 1/2 | Centering shuttering weather shade chajja----- |  | 400 | 400 | Item not sanctioned
EIS-1/4 | Providing 40x5 mm flat iron hold fast 40 cm long 30x10x15cm 1:3:6 mix (1 cement : 3 coarse sand : 6 graded stone aggregate 20mm nominal size) |  | 100 | 100 | Item not sanctioned
EIS-1/5 | 12 mm Plaster 1:4 |  | 150 | 150 | Item not sanctioned
EIS-1/6 | Providing and fixing bolts including nuts and washers complete. |  | 86 | 86 | Item not sanctioned
EIS-1/7 | Providing and fixing aluminium sub frame work for windows and ventilators with extruded built up standard tubular sections of approved make conforming to IS: 733 and IS: 1285, fixed with dash fastener of required dia and size (Dash fastener to be paid for separately). |  | 250 | 250 | Item not sanctioned
Signature of Contractor |  | Signature of JE |  | Signature of AE

## securedadv
ACCOUNTS OF SECURED ADVANCES (Referred to in Paragraphs 10.2.12)
Name of work: Construction of Studio Apartment at Cozy Cot at LBSNAA,Mussoorie. (EFC Scheme No.12 A of 12th Five Year Plan).
Division | MPD | SD-MPSD | Name of Contractor: Anil Dutt Sharma
Sl no. of this bill : 9th R.A. bill |  |  | Agmt. No. : 36/EE/MPD/2013-14 |  |  |  | Cash Book Voucher No. |  | Dated:
Accounts of Secured Advances allowed on the security of material brought to site
Qty. outstanding from the previous bill | Deduct-- qty. utilised in works measured since previous bill | Qty. outstanding I/c qty brought to site since previous bill | Full rate as asseseed by the D.O. | Descrip. Of material | Unit | Reduced rate at which advance is paid | Upto date Amt. Of advance | Ref. To D.O. written orders authorising the advance | Reasons for non clearance of advance when outstanding for more than three months
27960 | -5000 | 22960 | 47.16 | TMT BARS (REINFORCEMENT) | Kg | 42.07 | 965927
420.54 | 0 | 420.54 | 2582.4 | Lakha red granite | sqm | 2324.16 | 977402
0 | 0 | 972 | 968 | Vertified Tile | Cum | 871.2 | 846806
0 | 0 | 522 | 745.37 | Wall Tile | sqm | 670.83 | 350173
Total amount outstanding as per this account | [6 empty] | 3140308
Deduct- amount outstanding as per entry (C) of Annexure to previous bill | [6 empty] | -2153679
Net amount since previous bill | [6 empty] | 986629
*Entries relating to each description of materials should be posted this in column 3 first enter the difference between quantities in column 1 and 2 then show below this entry, the quantities if any brought to site against which a further advance has been
*Entries in coloumn 8 show the money values of the total quantities outstanding as per coloumn 3.
*Certified (1) that the plus quantities of materials shown in the coloumn 3 of the account above have actually been brought by the Contractor to the site of the work and the contractor has not prviously received any advance on their security (2) that thos
Dated Signature of the officer prepare bill |  |  |  |  | Dated Signature of officer authorising payment
*This certificate must be signed by the Sub-Divisional officer or Divisional Officer.
*This signature is necessary only when officer prepares the bill is not the officer who authorises the payment. In such a case the two signatures are essential.

## Sheet1
PART RATE STATEMENT |  |  |  |  | Annexure -I/1
Name of work:
Name of Contractor:
| Agmt. No. : /EE/MPD/2013-14 |  | Sl no. of this bill :
Item no. | BRIEF DESCRIPTION | Full rate | Part rate in previous bill | Part rate in this bill | Reason
Signature of Contractor |  | Signature of JE |  | Signature of AE